## Module Summary
Module Name | Frontend Status | Backend Status | Overall Status | Completed Features | Pending Work | Bug Count | Priority | Notes
Authentication and login approval | Partially Completed | Partially Completed | Partially Completed | Admin sign-in, staff password, approval queue, verbal code, and optional server-side approval bypass are implemented in screens and accounts APIs. | Alias words in credential check can select the first matching role. Runtime of the current screens was not executed in this audit. |  | Frontend: LoginScreen, OperatorWaitingScreen, VerbalOtpScreen, AdminPinSetupScreen, ApprovalQueueScreen. Backend: accounts/views.py and accounts/urls.py.
Staff and permissions | Partially Completed | Partially Completed | Partially Completed | Admin can maintain staff from StaffManagementScreen through /api/staff/. Staff records are forced to the staff role. | MenuRightsScreen.tsx is not mounted in App.tsx. This audit did not call the staff API. |  | frontend/src/screens/admin/StaffManagementScreen.tsx; backend/accounts/staff_views.py. Menu rights file is unused by App.tsx.
Branches | Partially Completed | Partially Completed | Partially Completed | Entity master lists and edits branches and their brands through the entities API. | Runtime was not executed in this audit. |  | EntityMasterScreen.tsx; backend/entities.
Brands | Partially Completed | Partially Completed | Partially Completed | Brand master and branch-brand links are implemented. | Runtime was not executed in this audit. |  | BrandMasterScreen.tsx; backend/brands; EntityBrand on the entity model.
Categories | Partially Completed | Partially Completed | Partially Completed | Category master uses the categories API. | Runtime was not executed in this audit. |  | CategoryMasterScreen.tsx; backend/categories.
Products | Partially Completed | Partially Completed | Partially Completed | Product catalogue reads products, categories, brands, and the selected branch. | Runtime was not executed in this audit. |  | ProductCatalogueScreen.tsx; backend/products.
Parties | Partially Completed | Partially Completed | Partially Completed | Customer master creates, updates, deactivates, and reactivates parties through the customers API. No separate supplier module was found. | PartyMasterScreen.tsx calls the masters API but is not mounted in App.tsx. |  | CustomerMasterScreen.tsx; backend/customers. Unused file: PartyMasterScreen.tsx.
Excel price lists | Partially Completed | Partially Completed | Partially Completed | Price list screen and Excel preview/commit endpoints exist, including quality-price rows. | Runtime of import was not executed in this audit. |  | PriceListScreen.tsx; PriceListImportModal.tsx; price_lists/views.py import_preview and import_commit.
PDF brand price lists | Pending | Pending | Pending | None. No screen imports a PDF price list. | BrandQualityPrice table and migration exist. No Python import uses pdfplumber and no PDF import action was found. |  | price_lists/models.py BrandQualityPrice; price_lists/migrations/0003_pdf_quality_prices.py; price_lists/views.py has Excel import only.
Purchase orders | Partially Completed | Partially Completed | Partially Completed | Purchase order list, entry, pipeline, and Excel import call the purchase-orders API. | Runtime was not executed in this audit. |  | PurchaseOrderScreen.tsx; PurchaseOrderImportModal.tsx; backend/purchase_orders.
Dispatch | Partially Completed | Partially Completed | Partially Completed | Dispatch list and Excel import call the dispatches API. | Runtime was not executed in this audit. |  | DispatchScreen.tsx; DispatchImportModal.tsx; backend/dispatches.
PO dispatch reconciliation | Pending | Partially Completed | Partially Completed | Backend GET /api/dispatches/reconciliation/ and PoDispatchReconciliationScreen.tsx exist. | App.tsx does not mount the screen, and IconRail does not link to it. |  | PoDispatchReconciliationScreen.tsx; dispatches/views.py reconciliation action; dispatches/reconciliation.py.
Invoices | Partially Completed | Partially Completed | Partially Completed | Invoice screen, trace panel, and PO invoice list call the invoices API. | Runtime was not executed in this audit. |  | InvoiceScreen.tsx; backend/invoices.
Payments and live adjustments | Partially Completed | Partially Completed | Partially Completed | Payment entry and the live adjustments screen call the payments API. | A second Payment Adjustment screen in the Vouchers menu is local sample state. Runtime of the live screen was not executed. |  | PaymentScreen.tsx; PaymentAdjustmentsScreen.tsx; backend/payments. Separate file PaymentAdjustmentScreen.tsx has no API import.
Notifications | Partially Completed | Partially Completed | Partially Completed | Notifications screen calls the notifications API. | Runtime was not executed in this audit. |  | NotificationsScreen.tsx; backend/notifications.
Party ledger and 360 | Partially Completed | Partially Completed | Partially Completed | Ledger, ledger PDF, and customer 360 call customer detail actions. | Runtime was not executed in this audit. |  | CustomerLedgerScreen.tsx; Customer360Screen.tsx; customers/views.py ledger, ledger/pdf, and 360 actions.
Dashboard | Partially Completed | Partially Completed | Partially Completed | Analytics dashboard calls /api/dashboards/admin/ and /api/dashboards/staff/ with the header period. | This audit did not load the dashboard in a browser. |  | AnalyticsDashboardScreen.tsx; dashboards/urls.py.
Operational reports | Partially Completed | Partially Completed | Partially Completed | Reports screen and party statement call report and customer statement endpoints. | Bad-debt monthly totals are still a code TODO. Runtime was not executed. |  | AnalyticsReportsScreen.tsx; BrandStatementReport.tsx; reports/urls.py; reports/services.py line 215.
Statutory reports | Pending | Pending | Pending | None. These screens do not call a report API. | Sales register, purchase register, trial balance, balance sheet, profit and loss, and bank/cash book render fixed sample rows. |  | SalesRegisterScreen.tsx, PurchaseRegisterScreen.tsx, TrialBalanceScreen.tsx, BalanceSheetScreen.tsx, ProfitAndLossScreen.tsx, BankCashBookScreen.tsx. Reachable from App.tsx.
Vouchers, notes, and returns | Pending | Pending | Pending | None. These screens do not call the payments or invoice API. | Bank receipt, cash receipt, payment voucher, credit note, debit note, material return, and the voucher-menu payment adjustment keep local sample state. |  | Screens 13, 14, 15, 17, 18, 19, and 20 in App.tsx. transactions models are registered in admin and seed data only.
Sales orders | Pending | Pending | Pending | None in the mounted application. | OrderFormScreen.tsx is local and is not mounted. OrderForm and SalesInvoice models have no API router. |  | OrderFormScreen.tsx; transactions/models.py; transactions/admin.py.
Inventory and stock | Pending | Pending | Pending | Item master stores a stock quantity field. | No stock-movement, warehouse, or adjustment module was found. |  | masters/models.py stock_quantity; ItemMasterScreen.tsx; masters/urls.py items route.
Legacy masters | Partially Completed | Partially Completed | Partially Completed | Item, group, parameter, chart of accounts, tax slab, and broker screens call /api/masters/ routes. | Each save path was not executed in this audit. These masters are separate from the live product and party masters. |  | ItemMasterScreen, GroupProductScreen, ParametersScreen, ChartOfAccountsScreen, TaxSlabMasterScreen, BrokerMasterScreen; backend/masters.
Backup | Pending | Pending | Pending | None. | BackupScreen keeps a local array and shows a success message. No backup command or download API is called. |  | frontend/src/screens/admin/BackupScreen.tsx, mounted as screen 9.
Year-end closing | Pending | Pending | Pending | None on the server. | The screen changes only the browser financial year and shows a rollover success message. |  | YearEndClosingScreen.tsx handleExecuteClosing, mounted as screen 10.
Audit log | Partially Completed | Partially Completed | Partially Completed | The screen lists audit rows held in browser context. Backend /api/auth/audit-trail exists. | The screen does not call that endpoint. Export only shows a toast. |  | AuditLogScreen.tsx; accounts/urls.py api/auth/audit-trail.
Deployment configuration | Not Verified | Not Verified | Not Verified | Not verified on a host. | Settings default DEBUG to true when DJANGO_DEBUG is unset. The host environment was not inspected. |  | backend/config/settings.py DEBUG, SECRET_KEY, and ALLOWED_HOSTS.

## Pending Work
Module Name | Pending Task | Why It Is Pending | Priority | Dependency | Evidence | Status
PDF brand price lists | Build PDF price-list preview and commit | The quality-price table exists, but no import action or screen reads a PDF. | High | Approved price-list table shape | price_lists/models.py BrandQualityPrice; no pdfplumber use in Python; views.py Excel actions only. | Pending
PO dispatch reconciliation | Mount the reconciliation screen in the application shell | The screen and API exist, but App.tsx never renders the screen. | High | Dispatch and purchase order APIs | App.tsx switch has no PoDispatchReconciliationScreen. dispatches/views.py exposes reconciliation. | Pending
Statutory reports | Replace sample statutory screens with ledger-backed reports | The mounted screens use fixed arrays and export buttons that only show a toast. | Critical | A real accounting ledger, which was not found behind these screens | SalesRegisterScreen.tsx initial state; BalanceSheetScreen.tsx export toast; same pattern in the other four files. | Pending
Vouchers, notes, and returns | Post vouchers through the API or remove the sample screens from navigation | Save actions update local state and show a posted message. They do not import an API client. | Critical | Payments and invoice balances | BankReceiptVoucherScreen.tsx showFlash says the bank book was updated. IconRail includes screens 13-20. | Pending
Sales orders | Implement a routed sales-order workflow or leave the unused screen out of scope | The order-form screen is not mounted and its save path is local. The OrderForm model has no API. | High | Party, product, and invoice design | OrderFormScreen.tsx is absent from App.tsx. transactions/models.py is used by admin and seed data. | Pending
Inventory and stock | Add stock movements or stop treating the item quantity as a stock module | Only MasterItem.stock_quantity exists. No receipt, issue, or adjustment flow was found. | High | Item master | masters/models.py stock_quantity; masters/urls.py items route. | Pending
Backup | Replace the local backup animation with a real database backup | The button prepends a row in component state and flashes a verified-snapshot message. | Critical | Database access and an operator-confirmed backup location | BackupScreen.tsx useState initial backups and setBackups. | Pending
Year-end closing | Implement a server-side year close or remove the screen | Execute only checks a browser PIN and then calls setFinancialYear. | Critical | Ledger close rules, which are not implemented | YearEndClosingScreen.tsx handleExecuteClosing. | Pending
Audit log | Load /api/auth/audit-trail and make export write a file | The visible grid reads ErpContext auditLogs. Export calls notifyInfo only. | High | Authentication audit endpoint | AuditLogScreen.tsx; accounts/urls.py path api/auth/audit-trail. | Pending
Staff and permissions | Decide whether menu rights stay out of the product | MenuRightsScreen.tsx is not imported by App.tsx. Staff maintenance itself is mounted. | Medium | Staff role model | App.tsx screen 7 is StaffManagementScreen. MenuRightsScreen has no other importer. | Pending
Operational reports | Populate bad-debt write-off totals | The report service leaves monthly write-off totals empty until a write-off module exists. | Medium | A write-off module, which was not found | reports/services.py TODO at the bad-debt totals. | Pending
Parties | Remove or redirect the unused party master screen | Customer master is the mounted party screen. PartyMasterScreen.tsx is not mounted. | Low | Customer master | App.tsx screen 23 is CustomerMasterScreen. PartyMasterScreen.tsx is not imported there. | Pending
Authentication and login approval | Remove role-word aliases from credential check | check_credentials maps staff, operator, bhavin, op-04, and user to the first active staff user before the password check. | High | None | accounts/views.py check_credentials alias list. | Pending
Dashboard | Load the admin dashboard in the browser | The screen calls the dashboard API. This audit did not open the page, so the current response was not seen. | High | Running frontend and backend | AnalyticsDashboardScreen.tsx dashboardsApi.admin call. | Not Verified
Parties | Click through header year and month on dated pages | Dated screens send the header period in code. This audit did not click the pages, so no data mismatch was reproduced. | Medium | Running frontend and backend | Period helpers and list screens pass from/to. Browser pass not done. | Not Verified
Deployment configuration | Inspect the host environment without recording secret values | Code defaults were read. The running host was not inspected, so production debug and secret state are unknown. | High | Access to the host environment | config/settings.py. No host process was queried. | Not Verified

## Bugs
Bug ID | Module Name | Bug Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Confirmed or Potential | Evidence | Status
B01 | Year-end closing | Any PIN of four or more characters is accepted, and the screen then reports that the financial year was locked and balances were rolled. | Open Year-End Closing, enter any PIN of at least four characters, and execute closing. | A wrong PIN is rejected, and a close writes the new year on the server. | The length check passes. The handler calls setFinancialYear('2026-27') and shows a success flash. No closing API is called. | Critical | Confirmed | YearEndClosingScreen.tsx handleExecuteClosing: pin !== '1984' && pin.length < 4. | Open
B02 | Backup | Backup reports that a full snapshot was generated and verified against a SHA-256 hash. | Open Backup and start a backup. | A database dump is created and can be restored. | The handler inserts a row into local component state and flashes success. No backup API is called. | High | Confirmed | BackupScreen.tsx setBackups and the verified-snapshot flash. | Open
B03 | Statutory reports | Sales register, purchase register, trial balance, balance sheet, profit and loss, and bank/cash book show fixed sample figures as the books. | Open any of those screens from the application shell. | Figures come from posted invoices, payments, and ledger balances. | Rows are written in the component, including named sample parties and amounts. Export actions only call showFlash. | High | Confirmed | SalesRegisterScreen.tsx useState invoices; PurchaseRegisterScreen.tsx; TrialBalanceScreen.tsx rows; BalanceSheetScreen.tsx; ProfitAndLossScreen.tsx; BankCashBookScreen.tsx. | Open
B04 | Vouchers, notes, and returns | Saving a bank receipt tells the user the bank book was updated, but the screen never calls the payments API. | Open Bank Receipt Voucher and save. The same local pattern is in cash receipt, payment voucher, credit note, debit note, material return, and voucher-menu payment adjustment. | The receipt is stored and allocated against live invoices. | BankReceiptVoucherScreen flashes that the voucher was posted and the bank book updated. The file does not import an API client. The other six screens likewise keep local state. | High | Confirmed | BankReceiptVoucherScreen.tsx showFlash; App.tsx cases 13, 14, 15, 17, 18, 19, 20. | Open
B05 | Sales orders | The order-form screen reports that orders were registered or committed. | The screen is not mounted, so this cannot be clicked from navigation. The handler is visible in source. | An order is stored through an API. | handleSimulateBulkImport and the register handler call showFlash. There is no sales-order API. | Medium | Confirmed | OrderFormScreen.tsx. Not referenced by App.tsx. | Open
B06 | Audit log | Export says it is exporting a signed CSV archive with a SHA256 checksum. | Open Audit Log and press export. | A file is downloaded from the audit endpoint. | The click handler only calls notifyInfo. The grid reads browser context, not /api/auth/audit-trail. | Medium | Confirmed | AuditLogScreen.tsx notifyInfo export label. | Open
B07 | Authentication and login approval | Credential check treats staff, operator, bhavin, bhavin.operator, op-04, and user as the first active staff account when that account's password matches. | POST the credential check with username staff and the password of the first active staff user. | Those words are rejected unless they are the real username. | The view replaces the username with the first staff user before check_password. | High | Confirmed | accounts/views.py check_credentials alias tuple. | Open
B08 | Deployment configuration | If DJANGO_DEBUG is unset, DEBUG is true and ALLOWED_HOSTS becomes all hosts. An empty secret falls back to a dev key only while DEBUG is true. | Not run against a host. | A deployed process has debug off, a private secret, and an explicit host list. | Not observed on a host. This is a code default, not a confirmed live exposure. | High | Potential | config/settings.py lines that read DJANGO_DEBUG and DJANGO_SECRET_KEY. Secret value was not copied. | Not Verified

## Completed Work
Module Name | Completed Feature | Verification Method | Evidence | Notes
Authentication and login approval | Admin login, staff login request, approval, verbal code, and session endpoints | Code inspection. Endpoints were not called in this audit. | accounts/urls.py auth routes; LoginScreen.tsx; VerbalOtpScreen.tsx; ApprovalQueueScreen.tsx through ErpContext. | Not marked Completed because runtime was not executed.
Staff and permissions | Staff list, create, update, and deactivate for admin | Code inspection. API was not called in this audit. | StaffManagementScreen.tsx; accounts/staff_views.py; accounts/urls.py staff router. | Menu rights are not part of this feature.
Branches | Branch master with brand links | Code inspection. | EntityMasterScreen.tsx; entities API router. | Runtime not executed.
Brands | Brand master and branch assignment | Code inspection. | BrandMasterScreen.tsx; brands API router. | Runtime not executed.
Categories | Category master | Code inspection. | CategoryMasterScreen.tsx; categories API router. | Runtime not executed.
Products | Product catalogue filtered by the selected branch | Code inspection of the screen and products API. | ProductCatalogueScreen.tsx; products API router. | Runtime not executed.
Parties | Party create, update, deactivate, reactivate, and permanent remove | Code inspection of CustomerMasterScreen handlers. | CustomerMasterScreen.tsx customersApi calls; customers API router. | No separate supplier master was found.
Excel price lists | Excel price-list preview and commit, including quality rows | Code inspection of the modal and view actions. | PriceListImportModal.tsx; price_lists/views.py import_preview and import_commit. | PDF import is not included.
Purchase orders | Purchase order list, entry, pipeline, and Excel import | Code inspection. | PurchaseOrderScreen.tsx; PurchaseOrderImportModal.tsx; purchase-orders router. | Runtime not executed.
Dispatch | Dispatch list and Excel import | Code inspection. | DispatchScreen.tsx; DispatchImportModal.tsx; dispatches router. | Runtime not executed.
PO dispatch reconciliation | Reconciliation query on the dispatch API | Code inspection of the view and service. | dispatches/views.py reconciliation; dispatches/reconciliation.py. | The screen is not mounted, so the user cannot open it.
Invoices | Invoice entry, list, and trace | Code inspection. | InvoiceScreen.tsx; invoices router. | Runtime not executed.
Payments and live adjustments | Payment entry and live payment adjustments | Code inspection. | PaymentScreen.tsx; PaymentAdjustmentsScreen.tsx; payments and payment-adjustments routers. | The voucher-menu adjustment screen is not this feature.
Notifications | Notification list | Code inspection. | NotificationsScreen.tsx; notifications router. | Runtime not executed.
Party ledger and 360 | Ledger, ledger PDF, and customer 360 | Code inspection of screen API calls and customer actions. | CustomerLedgerScreen.tsx; Customer360Screen.tsx; customers/views.py. | Runtime not executed.
Dashboard | Admin and staff dashboard requests scoped by header period | Code inspection of the screen request. | AnalyticsDashboardScreen.tsx; dashboards/urls.py. | The page was not loaded in this audit.
Operational reports | Trend, outstanding, performance, and party statement reports | Code inspection of report routes and the reports screen. | AnalyticsReportsScreen.tsx; BrandStatementReport.tsx; reports/urls.py; customers statement-report action. | Bad-debt write-off totals are still empty by TODO.
Legacy masters | Item, group, parameter, chart, tax slab, and broker API screens | Code inspection of API imports and masters routes. | Matching master screens; backend/masters/urls.py. | Save actions were not executed.
Audit log | Backend audit-trail route | Code inspection of the URL. | accounts/urls.py api/auth/audit-trail. | The mounted screen does not call it.

## Lists (hidden)
Completed | Critical | Confirmed | Open | Pending
Partially Completed | High | Potential | Fixed | In Progress
Pending | Medium |  | Not Verified | Blocked
Blocked | Low |  |  | Not Verified
Not Verified |  |  |  | Done